CONFIDENTIAL – NOT FOR DISTRIBUTION

(Prepared by and Property of PPM, Inc.)

Project Name:

Annandale School Renovation Project

Location:

Annandale, MN

Construction Budget Cost Estimate:

A/ E: Claybaugh

A/E Contact: Robert Claybaugh

A/E Commission No.: TBD

A/E Client: TBD

Summary of Contents:

Documents Provided

Assumptions & Qualifications

Proposed Construction Schedule

CSI Division Cost Summary

Gross Area Summary

Take-Off Breakdown

|  | Project Phase: |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Program Design Phase Budget Estimate |  |  |  |  |  |  |  |
|  | Date Prepared: |  |  |  | Number of Pages: |  |  |  |
|  | Mon, 10/21/13 |  |  |  | Pages 1 - 13 |  |  |  |
|  | Prepared By: |  |  |  | PPM Project No.: |  |  |  |
|  | Douglas L. Holmberg, PE/CPE |  |  |  | 1371.1361.003.ch.10.21.13 |  |  |  |
|  | President, PPM, Inc. |  |  |  |  |  |  |  |

Professional Project Management, Inc.

1858 East Shore Drive

St. Paul, MN 55109

- 919-4000 fax: (651) 774-0935 dougppm@gmail.com

Prepared By and Property of: PPM, Inc.

1858 East Shore Drive, St. Paul, MN 55109

(612) 919-4000	f: (651) 774-0935

© PPM Inc. 2013	1 of 13

CONFIDENTIAL – NOT FOR DISTRIBUTION

(Prepared by and Property of PPM, Inc.)

| Program Design Phase Budget Estimate |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Prepared by: |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project Name: Annandale School Renovation Project |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Professional Project Management, Inc. |  |  |  |  |
|  | Project Location: |  |  |  |  |  |  |  | Annandale, MN |  |  |  |  |  |  |  |  | Doug Holmberg, PE. |  |  | (612) 919-4000 |  |
|  | Date: | Mon, 10/21/13 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Architect: |  | Claybaugh |  |  |  |  |  |  | Arch. Commission No.: TBD |  |  |  | PPM Project No.: 1371.1361.003.ch.10.21.13 |  |  |  |  |  |  |  |  |
|  | CSI |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| DIVISION |  |  |  |  |  |  |  |  |  | DESCRIPTION |  |  | REMARKS | QUANTITY | UNIT | UNIT COST |  |  | SUBTOTAL |  | Lower Cost Range | Upper Cost Range |

Assumptions/Qualifications:

1. This Budget Estimate is based on the following:

|  | 2. Proposed Construction Schedule: |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Date of this Budget Estimate: |  |  | Monday, October 21, 2013 |  |
|  |  |  | Bid Opening: | Tue, | 12/03/13 |
|  |  | Start Construction: |  | Wed, | 01/01/14 |
|  |  | Construction Duration: |  | 10 |  |
|  |  | Complete Construction: |  | Mon, | 09/01/14 |
|  |  | Construction Midpoint: |  | Thu, | 05/01/14 |
|  | Duration from Budget Estimate date to Construction Midpoint: |  |  | 17 |  |
|  | Construction Cost Escalation Rate per month = |  |  | 0.40% |  |
|  | Construction Cost Escalation Rate per 12 month period = |  |  | 4.80% |  |

|  | Info: |  | Robert Claybaugh |  |
| --- | --- | --- | --- | --- |
| A/E Contact: |  |  |  |  |
| A/E Contact Phone No.: |  |  |  |  |
| NTP issued by: |  |  | Robert Claybaugh |  |
| Date NTP issued: |  |  | ??? |  |

Escalate 14 months of the mid point of construction

Construction Cost Escalation:

from Budget Estimate date to Construction Midpoint =	6.80%

3. Notes:

Updated Changes: 1361.ch.8.28.13

Updated Chases as of 1371.003.ch.10.21.13

|  | Construction Budget Summary: |  |  |  |  |  |  |  | Program Design Phase Budget Estimate |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 02000 | SITEWORK & DEMOLITION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 03000 | CONCRETE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 04000 | MASONRY |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 05000 | METALS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 06000 | WOOD & PLASTICS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 07000 | THERMAL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 08000 | DOORS, WINDOWS & GLASS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 09000 | FINISHES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 10000 | SPECIALTIES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 11000 | EQUIPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 12000 | FURNISHINGS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 13000 | SPECIAL CONSTRUCTION |  |  |  |  |  |  |  |  |  |  | Renovation Areas Only |  |  |  |  |  |  |  |  |  |
| 14000 | CONVEYING SYSTEMS |  |  |  |  |  |  |  |  | Lower Cost Range |  | Upper Cost Range |  |  | Lower Cost Range |  |  |  |  | Upper Cost Range |  |
| 15000 | MECHANICAL |  |  |  |  |  |  | % of Total Direct Cost = | 37.64% |  |  | 34.34% | $/s.f. = | $39.98 |  |  |  |  | $45.63 |  |  |
| 16000 | ELECTRICAL |  |  |  |  |  |  | % of Total Direct Cost = | 11.30% |  |  | 13.55% | $/s.f. = | $12.00 |  |  |  |  | $18.00 |  |  |

Renovation Area Totals

| Lower Cost |  |  |  |  |  |  |  |  |  |  | Upper Cost |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Range |  |  |  |  |  |  |  |  |  |  | Range |  |  |  |  |
|  |  |  |  | Total |  |  |  |  |  |  |  |  | Total |  |  |  |  |
| $712,015.50 |  |  |  |  |  |  |  |  |  |  | $1,001,537.50 |  |  |  |  |  |  |
| $0.00 |  |  |  |  |  |  |  |  |  |  | $0.00 |  |  |  |  |  |  |
| $16,770.00 |  |  |  |  |  |  |  |  |  |  | $22,360.00 |  |  |  |  |  |  |
| $16,800.00 |  |  |  |  |  |  |  |  |  |  | $21,000.00 |  |  |  |  |  |  |
| $0.00 |  |  |  |  |  |  |  |  |  |  | $0.00 |  |  |  |  |  |  |
| $145,700.00 |  |  |  |  |  |  |  |  |  |  | $183,250.00 |  |  |  |  |  |  |
| $616,000.00 |  |  |  |  |  |  |  |  |  |  | $658,000.00 |  |  |  |  |  |  |
| $604,800.00 |  |  |  |  |  |  |  |  |  |  | $815,465.00 |  |  |  |  |  |  |
| $0.00 |  |  |  |  |  |  |  |  |  |  | $0.00 |  |  |  |  |  |  |
| $0.00 |  |  |  |  |  |  |  |  |  |  | $0.00 |  |  |  |  |  |  |
| $0.00 |  |  |  |  |  |  |  |  |  |  | $0.00 |  |  |  |  |  |  |
| $0.00 |  |  |  |  |  |  |  |  |  |  | $0.00 |  |  |  |  |  |  |
| $200,000.00 |  |  |  |  |  |  |  |  |  |  | $250,000.00 |  |  |  |  |  |  |
| $1,704,643.50 |  |  |  |  |  |  |  |  |  |  | $1,945,447.00 |  |  |  |  |  |  |
| $511,644.00 |  |  |  |  |  |  |  |  |  |  | $767,466.00 |  |  |  |  |  |  |

Prepared By and Property of: PPM, Inc.

1858 East Shore Drive, St. Paul, MN 55109

(612) 919-4000	f: (651) 774-0935

© PPM Inc. 2013	2 of 13

|  |  |  |  |  |  |  |  |  |  |  |  |  |  | CONFIDENTIAL – NOT FOR DISTRIBUTION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | CSI |  |  |  |  |  |  |  |  |  |  |  |  |  | (Prepared |  |  |  |  |  | by and Property | of PPM, |  | Inc.) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | DIVISION |  |  |  |  |  |  |  |  | DESCRIPTION |  |  |  | REMARKS |  |  |  |  |  |  | QUANTITY | UNIT |  |  | UNIT COST |  |  | SUBTOTAL | Lower Cost Range |  |  |  |  |  | Upper Cost Range |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | TOTAL DIRECT COST |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | $4,528,373.00 |  |  |  |  |  | $5,664,525.50 |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Deduct Sales Tax |  |  |  | (Reduction = Total Direct Cost x 40% (Materials) x 0???%) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | $0.00 |  |  |  |  |  | $0.00 |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | Subtotal |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | $4,528,373.00 |  |  |  |  |  | $5,664,525.50 |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | General Conditions = |  |  | 10% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | $452,837.30 |  |  |  |  |  | $566,452.55 |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Subtotal |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | $ |  |  | 4,981,210.30 |  |  | $ |  | 6,230,978.05 |  |  |
|  |  |  |  |  |  |  |  |  |  |  | OH & Profit = |  | 4% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | $199,248.41 |  |  |  |  |  | $249,239.12 |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | Subtotal ( W/Out Contingencies ) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | $ |  |  | 5,180,458.71 |  |  | $ |  | 6,480,217.17 |  |  |
|  |  |  |  |  |  |  |  |  |  | Gross Square Foot Area |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 42,637 |  |  |  |  |  | 42,637 |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Cost Per Square Foot (Without Contingency) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | $121.50 |  |  |  |  |  | $151.99 |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  | Low |  |  |  |  |  |  | High |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | Design Contingency = |  |  | 10% |  |  |  |  |  |  |  | 15% |  |  |  |  |  |  |  | $518,045.87 |  |  |  |  |  | $972,032.58 |  |  |  |  |
|  |  |  |  |  |  |  |  | Total Construction Budget as of: |  |  |  |  | Monday, October 21, 2013 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | $5,698,504.58 |  |  |  |  |  | $7,452,249.75 |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Cost Per Square Foot (With Design Contingency) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | $133.65 |  |  |  |  |  | $174.78 |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | Construction Cost Escalation: |  |  | 6.80% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | $387,498.31 |  |  |  |  |  | $506,752.98 |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | Subtotal |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | $ |  |  | 6,086,002.89 |  |  | $ |  | 7,959,002.73 |  |  |
|  |  |  |  |  |  |  |  |  |  | Occupied Facility Factor / Contingency = |  |  | 0% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | $0.00 |  |  |  |  | $0.00 |
|  |  |  |  |  |  |  |  |  |  | Subtotal |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | $6,086,002.89 |  |  |  |  |  | $7,959,002.73 |  |  |  |  |
|  |  |  |  |  |  |  |  |  | TOTAL CONSTRUCTION BUDGET |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | $6,086,002.89 |  |  |  |  |  | $7,959,002.73 |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | as of Bid Day on: |  | $40,149.00 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | Cost Per SF as of Bid Day on |  |  | $40,149.00 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | $142.74 |  |  |  |  |  | $186.67 |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | Construction Contingency: |  |  |  | (NOT Included, By Owner!) |  |  |  |  |  |  | 0% | NOTE: PPM recommends 5% to 7% for renovation projects |  |  |  |  |  |  | $0.00 |  |  |  |  |  | $0.00 |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | Diversity Participation Contingency: |  |  |  | (NOT Included, By Owner!) |  |  |  |  |  |  | 0% | tbd ??? |  |  |  |  |  |  | $0.00 |  |  |  |  |  | $0.00 |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | TOTAL CONSTRUCTION BUDGET: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | $6,086,003 |  | $7,959,003 |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  | Projected to Completion Date of |  |  |  |  |  |  | Monday, September 1, 2014 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Total Lower Cost Range |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | $6,086,002.89 |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Average Renvation Cost |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  | Average Cost = |  |  |  |  |  |  |  |  |  |  |  |  |  |  | $7,022,503 |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Gross Square Foot Area |  |  |  | 42,637 |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Total Average Cost per SF = |  |  |  | $164.70 |  |  |  |  |  |  |  |  |  |  |

Prepared By and Property of: PPM, Inc.

1858 East Shore Drive, St. Paul, MN 55109

(612) 919-4000	f: (651) 774-0935

© PPM Inc. 2013	3 of 13

CONFIDENTIAL – NOT FOR DISTRIBUTION

| CSI |  |  |  |  |  |  |  |  | (Prepared |  | by and Property | of PPM, |  | Inc.) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| DIVISION |  |  |  |  |  |  | DESCRIPTION | REMARKS |  |  | QUANTITY | UNIT |  |  | UNIT COST |  | SUBTOTAL | Lower Cost Range | Upper Cost Range |

Deduct Alternate No. 1: Upper 2 Levels Remain Unoccupied - Windows Openings Insulated

|  |  |  |  |  |  |  | Add / Deduct Alternates: NOT Included in Budget Estimate!!! |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  |  |  |  | Lower Range |  |  | Upper Range |  |  | Lower Range |  |  | Upper Range |  |  |  |  |  |
|  |  |  | DEDUCT: |  |  |  |  |  |  |  |  |  | Unit Cost |  |  | Unit Cost |  |  | Cost |  |  | Cost |  |  |  |  |
|  |  |  |  | Ceilings, Walls & Flooring, Painting, Misc Finishes / Interior Build-Out |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | First Floor |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | Living Areas |  |  |  | 12,294 | sf | ($15.00) |  |  | ($20.00) |  |  | ($184,410.00) |  |  | ($245,880.00) |  |  |  |  |  |
|  |  |  |  |  | Second Floor |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | Living Areas |  |  |  | 12,327 | sf | ($15.00) |  |  | ($20.00) |  |  | ($184,905.00) |  |  | ($246,540.00) |  |  |  |  |  |
|  |  |  |  | Complete Mechanical: Air-Side and Wet-Side / Plumbing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | First Floor |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | Living Areas |  |  |  | 12,294 | sf | ($35.00) |  |  | ($40.00) |  |  | ($430,290.00) |  |  | ($491,760.00) |  |  |  |  |  |
|  |  |  |  |  | Second Floor |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | Living Areas |  |  |  | 12,327 | sf | ($35.00) |  |  | ($40.00) |  |  | ($431,445.00) |  |  | ($493,080.00) |  |  |  |  |  |
|  |  |  |  | Sprinkler |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | Renovation Areas |  |  |  | 24,621 | sf | ($2.50) |  |  | ($3.00) |  |  | ($61,552.50) |  |  | ($73,863.00) |  |  |  |  |  |
|  |  |  |  | Temperature Control |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | First Floor |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | Living Areas |  |  |  | 12,294 | sf | ($3.00) |  |  | ($3.00) |  |  | ($36,882.00) |  |  | ($36,882.00) |  |  |  |  |  |
|  |  |  |  |  | Second Floor |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | Living Areas |  |  |  | 12,327 | sf | ($3.00) |  |  | ($3.00) |  |  | ($36,981.00) |  |  | ($36,981.00) |  |  |  |  |  |
|  |  |  |  | Complete Electrical (Main Service: 2,500 Amp, 277/480V, Three Phase, Four Wire Distribution) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | First Floor |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | Living Areas |  |  |  | 12,294 | sf | $12.00 |  |  | $16.00 |  |  | $147,528.00 |  |  | $196,704.00 |  |  |  |  |  |
|  |  |  |  |  | Second Floor |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | Living Areas |  |  |  | 12,327 | sf | $12.00 |  |  | $16.00 |  |  | $147,924.00 |  |  | $197,232.00 |  |  |  |  |  |
|  |  |  | ADD: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | Window Infill |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Inill Window Openings with Sheathing and Insulation |  |  |  |  | 4,800 | sf | $2.00 |  |  | $5.00 |  |  | $9,600.00 |  |  | $24,000.00 |  |  |  |  |  |

Prepared By and Property of: PPM, Inc.

1858 East Shore Drive, St. Paul, MN 55109

(612) 919-4000	f: (651) 774-0935

© PPM Inc. 2013	4 of 13

CONFIDENTIAL – NOT FOR DISTRIBUTION

CSI

DIVISION

(Prepared by and Property of PPM, Inc.)

| DESCRIPTION | REMARKS | QUANTITY | UNIT | UNIT COST | SUBTOTAL | Lower Cost Range Upper Cost Range |  |
| --- | --- | --- | --- | --- | --- | --- | --- |

|  |  |  | Low Cost |  |  |  |  |  |  |  | High Cost |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Subtotal Deduct Alternate No. 1 = |  |  | ($1,061,413.50) |  |  |  |  |  |  | ($ |  | 1,207,050.00) |  |  |  |  |  |  |  |  |
|  | General Conditions: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 10.00% |  |  | ($106,141.35) |  |  |  |  |  |  | ($120,705.00) |  |  |  |  |  |  |  |  |  |  |
|  | Subtotal |  | ($1,167,554.85) |  |  |  |  |  |  |  | ($1,327,755.00) |  |  |  |  |  |  |  |  |  |
|  | OH & Profit: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4% |  |  | ($46,702.19) |  |  |  |  |  |  | ($53,110.20) |  |  |  |  |  |  |  |  |  |  |
| Subtotal ( W/Out Contingencies ) |  |  | ($1,214,257.04) |  |  |  |  |  |  |  | ($1,380,865.20) |  |  |  |  |  |  |  |  |  |
|  | Design Contingency: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 10.00% ($121,425.70) |  |  |  |  |  |  |  |  |  | ($138,086.52) |  |  |  |  |  |  |  |  |  |  |
|  | Total Construction Budget ($1,335,682.75) |  |  |  |  |  |  |  |  | ($1,518,951.72) |  |  |  |  |  |  |  |  |  |  |
|  | as of Bid Day on: |  | Tue, 12/03/13 |  |  |  |  |  |  | Fri, 01/01/04 |  |  |  |  |  |  |  |  |  |  |
|  | Cost Escalation: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6.80% |  |  | ($90,826.43) |  |  |  |  |  |  | ($103,288.72) |  |  |  |  |  |  |  |  |  |  |
|  | Subtotal = |  | ($1,426,509.18) |  |  |  |  |  |  | ($1,622,240.44) |  |  |  |  |  |  |  |  |  |  |

Add Alternate No. 2: Insulate Upper 2 levels exterior

|  |  |  |  |  |  |  |  | Add / Deduct Alternates: NOT Included in Budget Estimate!!! |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Lower Range |  |  | Higher Range |  |  | Lower Range |  |  | Higher Range |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Unit Cost |  |  |  | Unit Cost |  |  | Cost |  |  | Cost |  |  |  |  |
|  |  |  | ADD: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | Window |  |  |  | Infill |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Inill Window Openings with Sheathing and Insulation |  |  |  |  |  |  |  |  |  |  |  |  |  | 4,800 |  |  |  | sf | $2.00 |  |  | $5.00 |  |  | $9,600.00 |  |  | $24,000.00 |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Lower Range Cost |  |  |  |  |  |  |  | Higher Range Cost |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | Subtotal Deduct Alternate No. 3 = |  |  | $9,600.00 |  |  |  |  |  |  |  | $24,000.00 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  | General Conditions: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | 10.00% |  |  | $960.00 |  |  |  |  |  |  |  | $2,400.00 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Subtotal |  | $10,560.00 |  |  |  |  |  |  |  | $26,400.00 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  | OH & Profit: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | 4% |  |  | $422.40 |  |  |  |  |  |  |  | $1,056.00 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | Subtotal ( W/Out Contingencies ) |  |  | $10,982.40 |  |  |  |  |  |  |  | $27,456.00 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Design Contingency: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | 10.00% |  |  | $1,098.24 |  |  |  |  |  |  |  | $2,745.60 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Total Construction Budget |  | $12,080.64 |  |  |  |  |  |  |  | $30,201.60 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  | as of Bid Day on: |  | Fri, 01/01/04 |  |  |  |  |  |  |  | Fri, 01/01/04 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Cost Escalation: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | 6.80% |  |  | $821.48 |  |  |  |  |  |  |  | $2,053.71 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Prepared By and Property of: PPM, Inc.

1858 East Shore Drive, St. Paul, MN 55109

(612) 919-4000	f: (651) 774-0935

© PPM Inc. 2013	5 of 13

|  |  |  |  |  |  |  |  |  |  | CONFIDENTIAL – NOT FOR DISTRIBUTION |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | CSI |  |  |  |  |  |  |  |  |  | (Prepared |  | by and Property | of PPM, |  | Inc.) |  |  |  |  |
|  | DIVISION |  |  |  |  |  |  | DESCRIPTION |  | REMARKS |  |  | QUANTITY | UNIT |  | UNIT COST |  | SUBTOTAL | Lower Cost Range | Upper Cost Range |
|  |  |  |  |  |  |  |  |  | Subtotal = | $12,902.12 |  |  | $32,255.31 |  |  |  |  |  |  |  |

Add Alternate No. 3: Exterior Site Improvements

Add / Deduct Alternates: NOT Included in Budget Estimate!!!

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Lower Range |  |  | Higher Range |  |  | Lower Range |  |  | Higher Range |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Unit Cost |  |  |  | Unit Cost |  |  | Cost |  |  | Cost |  |  |
|  |  | ADD: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Site Demo: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | Remove existing top soil / landscaping at green spaces |  |  |  |  |  | 30,966 sf x 6'' /27 |  |  |  |  |  | 573 |  |  |  |  |  | cy | $4.00 |  |  | $8.00 |  |  | $2,293.78 |  |  | $4,587.56 |  |  |  |
|  |  |  |  | Remove Existing Asphalt Paving |  |  |  |  |  | 31,576 sf x 8'' / 27 |  |  |  |  |  | 784 |  |  |  |  |  | cy | $8.00 |  |  | $12.00 |  |  | $6,268.42 |  |  | $9,402.63 |  |  |  |
|  |  |  |  | Misc Grading Allowance |  |  |  |  |  |  |  |  |  |  |  | 1 |  |  |  |  |  | allow | $5,000.00 |  |  | $10,000.00 |  |  | $5,000.00 |  |  | $10,000.00 |  |  |  |
|  |  |  | New Sitework: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | New Topsoil at green spaces |  |  |  |  |  | 30,966 sf x 4'' /27 |  |  |  |  |  | 378 |  |  |  |  |  | cy | $12.00 |  |  | $15.00 |  |  | $4,541.68 |  |  | $5,677.10 |  |  |  |
|  |  |  |  | New Sodding at Green Spaces (not complete replacing) |  |  |  |  |  | 30,966 / 9 |  |  |  |  |  | 3,441 |  |  |  |  |  | sy | $1.50 |  |  | $2.50 |  |  | $5,161.00 |  |  | $8,601.67 |  |  |  |
|  |  |  |  | Misc Landscaping Allowance at Parking area |  |  |  |  |  |  |  |  |  |  |  | 1 |  |  |  |  |  | allow | $3,000.00 |  |  | $8,000.00 |  |  | $3,000.00 |  |  | $8,000.00 |  |  |  |
|  |  |  |  | Sight Lighting Allowance |  |  |  |  |  |  |  |  |  |  |  | 1 |  |  |  |  |  | allow | $5,000.00 |  |  | $8,000.00 |  |  | $5,000.00 |  |  | $8,000.00 |  |  |  |
|  |  |  |  | New Concrete Walks |  |  |  |  |  |  |  |  |  |  |  | 1,060 |  |  |  |  |  | sf | $3.00 |  |  | $4.00 |  |  | $3,180.00 |  |  | $4,240.00 |  |  |  |
|  |  |  | New Uncovered Parking Area |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | New Base Course |  |  |  |  |  | 23,029 sf x 6'' / 27 |  |  |  |  |  | 426 |  |  |  |  |  | cy | $12.00 |  |  | $15.00 |  |  | $5,117.56 |  |  | $6,396.94 |  |  |  |
|  |  |  |  | New Asphalt Paving |  |  |  |  |  | 23,029 sf / 9 |  |  |  |  |  | 2,559 |  |  |  |  |  | sy | $12.00 |  |  | $14.00 |  |  | $30,705.33 |  |  | $35,822.89 |  |  |  |
|  |  |  |  | New Curb & Gutter |  |  |  |  |  |  |  |  |  |  |  | 983 |  |  |  |  |  | lf | $12.00 |  |  | $15.00 |  |  | $11,796.00 |  |  | $14,745.00 |  |  |  |
|  |  |  |  | New Painted Stalls |  |  |  |  |  |  |  |  |  |  |  | 43 |  |  |  |  |  | ea | $10.00 |  |  | $15.00 |  |  | $430.00 |  |  | $645.00 |  |  |  |
|  |  |  | New Covered Parking Area |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | Unheated Parking Garage - 18 stalls |  |  |  |  |  |  |  |  |  |  |  | 3,748 |  |  |  |  |  | sf | $110.00 |  |  | $140.00 |  |  | $412,280.00 |  |  | $524,720.00 |  |  |  |
|  |  |  |  |  |  |  |  |  |  | Lower Range Cost |  |  |  |  |  | Higher Range Cost |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | Subtotal Deduct Alternate No. 3 = |  |  | $494,773.77 |  |  |  |  |  | $640,838.79 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | General Conditions: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | 10.00% |  |  | $49,477.38 |  |  |  |  |  | $64,083.88 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | Subtotal |  | $544,251.14 |  |  |  |  |  | $704,922.67 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | OH & Profit: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | 4% |  |  | $21,770.05 |  |  |  |  |  | $28,196.91 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | Subtotal ( W/Out Contingencies ) |  |  | $566,021.19 |  |  |  |  |  | $733,119.57 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | Design Contingency: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | 10.00% |  |  | $56,602.12 |  |  |  |  |  | $73,311.96 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | Total Construction Budget |  | $622,623.31 |  |  |  |  |  | $806,431.53 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | as of Bid Day on: |  | Fri, 01/01/04 |  |  |  |  |  | Fri, 01/01/04 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | Cost Escalation: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | 6.80% |  |  | $42,338.39 |  |  |  |  |  | $54,837.34 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | Subtotal = |  | $664,961.69 |  |  |  |  |  | $861,268.87 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Prepared By and Property of: PPM, Inc.

1858 East Shore Drive, St. Paul, MN 55109

(612) 919-4000	f: (651) 774-0935

© PPM Inc. 2013	6 of 13

CONFIDENTIAL – NOT FOR DISTRIBUTION

| CSI |  |  |  |  |  |  |  |  | (Prepared |  | by and Property | of PPM, |  | Inc.) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| DIVISION |  |  |  |  |  |  | DESCRIPTION | REMARKS |  |  | QUANTITY | UNIT |  |  | UNIT COST |  | SUBTOTAL | Lower Cost Range | Upper Cost Range |

|  |  |  |  |  |  |  | TOTAL DIRECT COST SUMMARY: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  | (Quantity Take-Off) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | Gross Areas: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | PPM |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Mon, 10/21/13 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Renovation Areas |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | Basement Level |  |  |  |  |  |  |  |  |  |  |  |  |  | (Square Feet) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Boiler Room |  |  |  | 1,260 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Gym |  |  |  | 4,431 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | School Area |  |  |  | 12,325 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | First Floor |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Living Areas |  |  |  | 12,294 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | Second Floor |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Living Spaces |  |  |  | 12,327 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | Subtotal Renovation Areas = |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 42,637 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Total Gross Area |  |  |  |  |  |  |  | 42,637 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Renovation |  |  |  |  |
| 02000 | SITEWORK & DEMOLITION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Lower Range |  |  | Upper Range |  |  | Lower Range |  |  | Upper Range |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Unit Cost |  |  |  | Unit Cost |  |  | Cost |  |  | Cost |  |  |
|  | Demolition & Clearing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | SITE DEMO |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | TBD |  |  |  |  |  |  |  | 0 | allow | $10,000.00 |  |  | $15,000.00 |  |  | $0.00 |  |  | $0.00 |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Low Cost |  |  |  | High Cost |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | Subtotal Site Demolition & Clearing = |  |  |  |  |  |  |  |  |  |  | $0.00 |  |  |  |  | $0.00 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | NOTE: The Following Costs ARE NOT Included |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | 1. Contaminated Soil Abatement / Remediation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ea | $0.00 |  |  |  |  |  | $0.00 |  |  |  |  |  |  |
|  |  |  |  |  |  |  | 2. Hazardous Material Abatement / Remediation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ea | $0.00 |  |  |  |  |  | $0.00 |  |  |  |  |  |  |
|  |  |  |  |  |  |  | 3. Soils Correction |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ea | $0.00 |  |  |  |  |  | $0.00 |  |  |  |  |  |  |
|  | Building Demolition / Prep |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Exterior Demoliition |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Exterior Masonry Repair |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Allowance |  |  |  |  |  |  |  | 1 | sf | $30,000.00 |  |  | $40,000.00 |  |  | $30,000.00 |  |  | $40,000.00 |  |  |  |
|  |  |  | Demolish Existing Boiler Building |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1,045 sf x 13' |  |  |  |  |  |  |  | 13,585 | cf | $0.30 |  |  | $0.50 |  |  | $4,075.50 |  |  | $6,792.50 |  |  |  |

Prepared By and Property of: PPM, Inc.

1858 East Shore Drive, St. Paul, MN 55109

(612) 919-4000	f: (651) 774-0935

© PPM Inc. 2013	7 of 13

|  |  |  |  |  |  |  |  |  |  |  |  | CONFIDENTIAL – NOT FOR DISTRIBUTION |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | CSI |  |  |  |  |  |  |  |  |  |  |  | (Prepared |  | by and Property | of PPM, |  | Inc.) |  |  |  |  |  |  |
|  | DIVISION |  |  |  |  |  |  |  |  |  | DESCRIPTION | REMARKS |  |  | QUANTITY | UNIT |  |  | UNIT COST |  |  | SUBTOTAL | Lower Cost Range | Upper Cost Range |
|  |  |  |  |  | Remove Exterior Windows |  |  |  |  |  |  |  |  |  | 7,000 | sf |  |  | $7.00 |  | $9.00 | $49,000.00 | $63,000.00 |  |
|  |  |  |  | Roofing Demo |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Remove exiting roofing system |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | Boiler Building |  |  |  |  |  |  |  |  | 1,115 | sf |  |  | $2.00 |  | $4.00 | $2,230.00 | $4,460.00 |  |
|  |  |  |  |  |  | Gym |  |  |  |  |  |  |  |  | 4,583 | sf |  |  | $2.00 |  | $3.00 | $9,166.00 | $13,749.00 |  |
|  |  |  |  |  |  | Main Building |  |  |  |  |  |  |  |  | 12,327 | sf |  |  | $2.00 |  | $3.00 | $24,654.00 | $36,981.00 |  |
|  |  |  |  |  | Demo Exiting Roof Hatch |  |  |  |  |  |  | Allowance |  |  | 1 | sf |  |  | $500.00 |  | $1,000.00 | $500.00 | $1,000.00 |  |
|  |  |  |  | Interior Demolition |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Hazardous Material Abatement |  |  |  |  |  |  | Allowance by A/E |  |  | 1 | sf |  |  | $166,000.00 |  | $166,000.00 | $166,000.00 | $166,000.00 |  |
|  |  |  |  |  | Demo Interior Finishes, Mechanical, and Electrical Systems |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | Boiler Building |  |  |  |  |  |  |  |  | 1,260 | sf |  |  | $10.00 |  | $15.00 | $12,600.00 | $18,900.00 |  |
|  |  |  |  |  |  | Gym |  |  |  |  |  |  |  |  | 4,431 | sf |  |  | $10.00 |  | $15.00 | $44,310.00 | $66,465.00 |  |
|  |  |  |  |  |  | Main Building |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | Basement |  |  |  |  |  |  | 12,325 | sf |  |  | $10.00 |  | $15.00 | $123,250.00 | $184,875.00 |  |
|  |  |  |  |  |  |  |  | First Floor |  |  |  |  |  |  | 12,294 | sf |  |  | $10.00 |  | $15.00 | $122,940.00 | $184,410.00 |  |
|  |  |  |  |  |  |  |  | Second Floor |  |  |  |  |  |  | 12,327 | sf |  |  | $10.00 |  | $15.00 | $123,270.00 | $184,905.00 |  |
|  |  |  |  |  |  |  |  |  |  |  |  | Low Cost |  |  | High Cost |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Subtotal Building Demo / Prep = | $711,995.50 |  |  | $971,537.50 |  |  |  |  |  |  |  |  |  |
|  |  |  | Site |  | Work |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | New Site Work |  |  |  |  |  |  |  | TBD |  |  | 0 | sf |  |  | $0.00 |  | $0.00 | $0.00 | $0.00 |  |
|  |  |  |  | New Access Entry - excavation and partial floor replacement neede |  |  |  |  |  |  |  | Allowance |  |  | 1 | allow |  |  | $20.00 |  | $30,000.00 | $20.00 | $30,000.00 |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Renovation |  |
|  |  |  |  |  |  |  |  |  |  |  | Subtotal Sitework & Demolition |  |  |  |  |  |  |  |  |  |  |  | $712,015.50 | $1,001,537.50 |
|  | 03000 |  | CONCRETE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Renovation |  |
|  |  |  |  |  |  |  |  |  |  |  | Subtotal Concrete |  |  |  |  |  |  |  |  |  |  |  | $0.00 | $0.00 |
|  | 04000 |  | MASONRY |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Exterior Masonry Walls |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | Infill East Wall with CMU & Brick Veneer |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Basement Level |  |  |  |  |  |  | 43 lf x 13' |  |  | 559 | sf |  |  | $30.00 |  | $40.00 | $16,770.00 | $22,360.00 |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Renovation |  |
|  |  |  |  |  |  |  |  |  |  |  | Subtotal Masonry |  |  |  |  |  |  |  |  |  |  |  | $16,770.00 | $22,360.00 |

Prepared By and Property of: PPM, Inc.

1858 East Shore Drive, St. Paul, MN 55109

(612) 919-4000	f: (651) 774-0935

© PPM Inc. 2013	8 of 13

|  |  |  |  |  |  |  |  |  |  |  |  | CONFIDENTIAL – NOT FOR DISTRIBUTION |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CSI |  |  |  |  |  |  |  |  |  |  |  |  | (Prepared |  | by and Property | of PPM, |  | Inc.) |  |  |  |  |  |  |
| DIVISION |  |  |  |  |  |  |  |  |  |  | DESCRIPTION | REMARKS |  |  | QUANTITY | UNIT |  |  | UNIT COST |  |  | SUBTOTAL | Lower Cost Range | Upper Cost Range |
| 05000 |  | METALS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | New Raised Floor Area |  |  |  |  |  |  |  |  | 600 | sf |  |  | $28.00 |  | $35.00 | $16,800.00 | $21,000.00 |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Renovation |  |
|  |  |  |  |  |  |  |  |  |  |  | Subtotal Metals |  |  |  |  |  |  |  |  |  |  |  | $16,800.00 | $21,000.00 |
| 06000 |  | WOOD & PLASTICS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Renovation |  |
|  |  |  |  |  |  |  |  |  |  |  | Subtotal Wood & Plastic |  |  |  |  |  |  |  |  |  |  |  | $0.00 | $0.00 |
| 07000 |  | THERMAL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Built-Up Roofing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Fully Adhered Roofing System w/ sheathing and Insulation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | Boiler Building |  |  |  |  |  |  |  |  | 1,115 | sf |  |  | $8.00 |  | $10.00 | $8,920.00 | $11,150.00 |  |
|  |  |  |  |  |  | Gym |  |  |  |  |  |  |  |  | 4,583 | sf |  |  | $8.00 |  | $10.00 | $36,664.00 | $45,830.00 |  |
|  |  |  |  |  |  | Main Building |  |  |  |  |  |  |  |  | 12,327 | sf |  |  | $8.00 |  | $10.00 | $98,616.00 | $123,270.00 |  |
|  |  |  | New Roof Hatch |  |  |  |  |  |  |  |  |  |  |  | 1 | sf |  |  | $1,500.00 |  | $3,000.00 | $1,500.00 | $3,000.00 |  |
|  |  |  | Skylight Replacement - TBD |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Renovation |  |
|  |  |  |  |  |  |  |  |  |  |  | Subtotal Thermal |  |  |  |  |  |  |  |  |  |  |  | $145,700.00 | $183,250.00 |
| 08000 |  | Doors, Windows & Glass |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Doors |  |  |  |  |  |  |  |  | Refinish Existing doors, replace entry doors - incuded | with renovation costs below |  |  |  |  |  |  |  |  |  |  |  |  |
| ??? |  | Wood Windows |  |  |  |  |  |  |  |  |  | Allowance??? |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Wood Storefront |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | Exterior Windows |  |  |  |  |  | New exterior windows |  |  | 7,000 | sf |  |  | $88.00 |  | $94.00 | $616,000.00 | $658,000.00 |  |

Prepared By and Property of: PPM, Inc.

1858 East Shore Drive, St. Paul, MN 55109

(612) 919-4000	f: (651) 774-0935

© PPM Inc. 2013	9 of 13

|  |  |  |  |  |  |  |  |  |  |  | CONFIDENTIAL – NOT FOR DISTRIBUTION |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | CSI |  |  |  |  |  |  |  |  |  |  | (Prepared |  | by and Property | of PPM, |  | Inc.) |  |  |  |  |  |  |
|  | DIVISION |  |  |  |  |  |  |  | DESCRIPTION |  | REMARKS |  |  | QUANTITY | UNIT |  |  | UNIT COST |  |  | SUBTOTAL | Lower Cost Range | Upper Cost Range |
|  |  |  | Misc. Doors, Windows & Glass Allowance |  |  |  |  |  |  |  |  |  |  |  | ea |  |  | $0.00 |  |  | $0.00 |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Renovation |  |
|  |  |  |  |  |  |  |  |  | Subtotal Doors, Windows & Glass |  |  |  |  |  |  |  |  |  |  |  |  | $616,000.00 | $658,000.00 |
|  | 09000 |  | Finishes |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | Ceilings, Walls & Flooring, Painting, Misc Finishes / Interior Build-O |  |  |  |  |  |  | ut |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Basement Level |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | Boiler Room |  |  |  |  |  |  |  | 1,260 | sf |  |  | $5.00 |  | $8.00 | $6,300.00 | $10,080.00 |  |
|  |  |  |  |  |  | Gym |  |  |  |  |  |  |  | 4,431 | sf |  |  | $10.00 |  | $15.00 | $44,310.00 | $66,465.00 |  |
|  |  |  |  |  |  | School Area |  |  |  |  |  |  |  | 12,325 | sf |  |  | $15.00 |  | $20.00 | $184,875.00 | $246,500.00 |  |
|  |  |  |  |  | First Floor |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | Living Areas |  |  |  |  |  |  |  | 12,294 | sf |  |  | $15.00 |  | $20.00 | $184,410.00 | $245,880.00 |  |
|  |  |  |  |  | Second Floor |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | Living Spaces |  |  |  |  |  |  |  | 12,327 | sf |  |  | $15.00 |  | $20.00 | $184,905.00 | $246,540.00 |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Renovation |  |
|  |  |  |  |  |  |  |  |  |  | Subtotal Finishes |  |  |  |  |  |  |  |  |  |  |  | $604,800.00 | $815,465.00 |
|  | 10000 |  | SPECIALTIES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Renovation |  |
|  |  |  |  |  |  |  |  |  |  | Subtotal Specialties |  |  |  |  |  |  |  |  |  |  |  | $0.00 | $0.00 |
|  | 11000 |  | EQUIPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Renovation |  |
|  |  |  |  |  |  |  |  |  |  | Subtotal Equipment |  |  |  |  |  |  |  |  |  |  |  | $0.00 | $0.00 |
|  | 12000 |  | FURNISHINGS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Misc. Allowance |  |  |  |  |  |  |  | Allowance |  |  |  | ea |  |  | $0.00 |  |  | $0.00 |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Renovation |  |
|  |  |  |  |  |  |  |  |  |  | Subtotal Furnishings |  |  |  |  |  |  |  |  |  |  |  | $0.00 | $0.00 |
|  | 13000 |  | SPECIAL CONSTRUCTION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Renovation |  |
|  |  |  |  |  |  |  |  |  | Subtotal Special Construction |  |  |  |  |  |  |  |  |  |  |  |  | $0.00 | $0.00 |

Prepared By and Property of: PPM, Inc.

1858 East Shore Drive, St. Paul, MN 55109

(612) 919-4000	f: (651) 774-0935

© PPM Inc. 2013	10 of 13

|  |  |  |  |  |  |  |  |  |  | CONFIDENTIAL – NOT FOR DISTRIBUTION |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | CSI |  |  |  |  |  |  |  |  |  | (Prepared |  | by and Property | of PPM, |  | Inc.) |  |  |  |  |  |  |
|  | DIVISION |  |  |  |  |  |  |  | DESCRIPTION | REMARKS |  |  | QUANTITY | UNIT |  |  | UNIT COST |  |  | SUBTOTAL | Lower Cost Range | Upper Cost Range |
|  | 14000 |  | CONVEYING SYSTEMS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Elevators |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | Hydraulic, Front & Rear Entry |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Passenger - 5-Stop |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | 5-Stop Basement (Difficult Construction |  |  |  |  |  |  | 5 | stop |  |  | $30,000.00 |  | $35,000.00 | $150,000.00 | $175,000.00 |  |
|  |  |  |  | Hoistway |  |  |  |  |  |  |  |  | 5 | stop |  |  | $10,000.00 |  | $15,000.00 | $50,000.00 | $75,000.00 |  |
|  |  |  |  |  | Hoistway |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Renovation |  |
|  |  |  |  |  |  |  |  |  | Subtotal Conveying Systems |  |  |  |  |  |  |  |  |  |  |  | $200,000.00 | $250,000.00 |
|  | 15000 |  | MECHANICAL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Complete Mechanical: Air-Side and Wet-Side / Plumbing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | Air Side |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Basement |  |  |  | Level |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | Boiler Room |  |  |  |  |  |  | 1,260 | sf |  |  | $35.00 |  | $45.00 | $44,100.00 | $56,700.00 |  |
|  |  |  |  |  |  | Gym |  |  |  |  |  |  | 4,431 | sf |  |  | $30.00 |  | $35.00 | $132,930.00 | $155,085.00 |  |
|  |  |  |  |  |  | School Area |  |  |  |  |  |  | 12,325 | sf |  |  | $35.00 |  | $40.00 | $431,375.00 | $493,000.00 |  |
|  |  |  |  |  | First Floor |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | Living Areas |  |  |  |  |  |  | 12,294 | sf |  |  | $35.00 |  | $40.00 | $430,290.00 | $491,760.00 |  |
|  |  |  |  |  | Second Floor |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | Living Spaces |  |  |  |  |  |  | 12,327 | sf |  |  | $35.00 |  | $40.00 | $431,445.00 | $493,080.00 |  |
|  |  |  |  |  |  |  |  |  | Subtotal Complete Mechanical = | $1,470,140.00 |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Cost / SF = | #REF! |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Plumbing |  |  |  |  |  | Include Above |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Subtotal Plumbing = | $0.00 |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Plumbing Cost / SF = | #REF! |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Hydronics (included in HVAC "Wet Side") |  |  |  |  |  |  | Included Above! |  |  |  | ea |  |  | $0.00 |  |  | $0.00 |  |  |
|  |  |  | Sprinkler |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Renovation Areas |  |  |  |  |  |  |  | 42,637 | sf |  |  | $2.50 |  | $3.00 | $106,592.50 | $127,911.00 |  |
|  |  |  |  |  |  |  |  |  | Subtotal Sprinkler = | $106,592.50 |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | Temperature Control |  |  |  |  |  | DDC Control System |  |  |  | sf |  |  | $3.00 |  |  | $0.00 |  |  |
|  |  |  |  |  | Basement Level |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | Boiler Room |  |  |  |  |  |  | 1,260 | sf |  |  | $3.00 |  | $3.00 | $3,780.00 | $3,780.00 |  |
|  |  |  |  |  |  | Gym |  |  |  |  |  |  | 4,431 | sf |  |  | $3.00 |  | $3.00 | $13,293.00 | $13,293.00 |  |
|  |  |  |  |  |  | School Area |  |  |  |  |  |  | 12,325 | sf |  |  | $3.00 |  | $3.00 | $36,975.00 | $36,975.00 |  |
|  |  |  |  |  | First Floor |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | Living Areas |  |  |  |  |  |  | 12,294 | sf |  |  | $3.00 |  | $3.00 | $36,882.00 | $36,882.00 |  |

Prepared By and Property of: PPM, Inc.

1858 East Shore Drive, St. Paul, MN 55109

(612) 919-4000	f: (651) 774-0935

© PPM Inc. 2013	11 of 13

|  |  |  |  |  |  |  |  |  |  |  |  | CONFIDENTIAL – NOT FOR DISTRIBUTION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | CSI |  |  |  |  |  |  |  |  |  |  |  | (Prepared |  |  | by and Property | of PPM, |  | Inc.) |  |  |  |  |  |  |  |  |
|  | DIVISION |  |  |  |  |  |  |  |  | DESCRIPTION |  |  | REMARKS |  |  | QUANTITY | UNIT |  |  | UNIT COST |  |  | SUBTOTAL |  | Lower Cost Range | Upper Cost Range |  |
|  |  |  |  |  | Second Floor |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | Living Spaces |  |  |  |  |  |  |  |  |  | 12,327 | sf |  |  | $3.00 |  | $3.00 | $36,981.00 |  | $36,981.00 |  |  |
|  |  |  | Misc. Mechanical Allowance |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | Renovation Area |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Renovation |  |  |
|  |  |  |  |  |  |  |  |  |  | Subtotal Mechanical |  |  |  |  |  |  |  |  |  |  |  |  |  |  | $1,704,643.50 | $1,945,447.00 |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Total Mechanical Cost/sf = |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | % of Total Construction Budget = |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 16000 |  | ELECTRICAL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Complete Electrical (Main Service: 2,500 Amp, 277/480V, Three Phase, Four Wire Distribution) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Basement Level |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | Boiler Room |  |  |  |  |  |  |  |  |  | 1,260 | sf |  |  | $12.00 |  | $18.00 | $15,120.00 |  | $22,680.00 |  |  |
|  |  |  |  |  |  | Gym |  |  |  |  |  |  |  |  |  | 4,431 | sf |  |  | $12.00 |  | $18.00 | $53,172.00 |  | $79,758.00 |  |  |
|  |  |  |  |  |  | School Area |  |  |  |  |  |  |  |  |  | 12,325 | sf |  |  | $12.00 |  | $18.00 | $147,900.00 |  | $221,850.00 |  |  |
|  |  |  |  |  | First Floor |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | Living Areas |  |  |  |  |  |  |  |  |  | 12,294 | sf |  |  | $12.00 |  | $18.00 | $147,528.00 |  | $221,292.00 |  |  |
|  |  |  |  |  | Second Floor |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | Living Spaces |  |  |  |  |  |  |  |  |  | 12,327 | sf |  |  | $12.00 |  | $18.00 | $147,924.00 |  | $221,886.00 |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Renovation |  |  |
|  |  |  |  |  |  |  |  |  |  | Subtotal Electrical |  |  |  |  |  |  |  |  |  |  |  |  |  |  | $511,644.00 | $767,466.00 |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Total Electrical Cost/sf | = |  |  |  |  |  |  |  |  |  |  | $12.00 |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | % of Total Construction Budget = |  |  |  |  |  |  |  |  |  |  |  | 8.98% |  |  |
|  |  |  |  |  |  |  |  |  | ITEMS NOT INCLUDED IN BUDGET ESTIMATE: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  | 1. Items specifically not listed above but not |  |  | limited to the following: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  | 2. Design Contingency to be determined by Architect & Owner |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  | 3. Construction Contingency to be determined by Architect & Owner |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  | 4. Design Fees |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  | 5. | Consultant Reimbursables |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  | 6. Owner Provided Items |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  | 7. Owner Soft Costs |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  | 8. | Furniture |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  | NOTE: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Professional Project Management, Inc. cannot and does |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  | not warrant or represent the accuracy of this budget |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  | estimate. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  | The above materials including budget estimate |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  | format and budget cost information have been |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  | developed by Professional Project Management, Inc. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  | All rights are reserved and no part of this document |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Prepared By and Property of: PPM, Inc. |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | MN 55109 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1858 East Shore Drive, St. Paul, |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | (612) 919-4000 f: (651) 774-0935 |  |  |

© PPM Inc. 2013	12 of 13

CONFIDENTIAL – NOT FOR DISTRIBUTION

|  | CSI |  |  |  |  |  |  |  |  |  |  | (Prepared |  | by and Property | of PPM, |  | Inc.) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | DIVISION |  |  |  |  |  |  |  | DESCRIPTION |  | REMARKS |  |  | QUANTITY | UNIT |  |  | UNIT COST |  | SUBTOTAL | Lower Cost Range | Upper Cost Range |
|  |  |  |  |  |  |  |  |  | may be reproduced and/or distributed without |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  | the express permission in writing of Professional |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Project Management, Inc. |  |  |  |  |  |  |  |  |  |  |  |  |  |

Prepared By and Property of: PPM, Inc.

1858 East Shore Drive, St. Paul, MN 55109

(612) 919-4000	f: (651) 774-0935

© PPM Inc. 2013	13 of 13